## Executive Summary
CCP-Frontend — 30-Day Development Roadmap
Owner: Incoming Lead Frontend Developer ¦ Start: 2026-05-01 ¦ End: 2026-06-11 (30 working days)
Mission
Take ownership of a working Next.js 15 / React 19 client for the CCP payments platform, eliminate critical UX risks around money flows (double-submits, stale balances, broken token refresh), establish production-grade observability, type safety, performance budgets, and CI, and ship one new feature end-to-end (MFA + fraud step-up). The codebase is healthy — this plan stabilizes, hardens, optimizes, then advances. Mirrors the backend 30-day roadmap day-for-day so leads can coordinate.
Phases
Phase | Window | Focus
Phase 1 – Stabilize | Days 1–7 | Run locally, fix double-submit + auth refresh races, wire Sentry + Replay, set up Vitest + RTL + MSW.
Phase 2 – Harden | Days 8–14 | CI pipeline, TS strict + zod from OpenAPI, error boundaries, Web Vitals, CSP + security headers, dep scan.
Phase 3 – Optimize | Days 15–21 | Bundle audit, RSC migration, React Query strategy, image/font, Lighthouse CI, browser tracing → backend.
Phase 4 – Advance | Days 22–30 | Storybook + visual regression, Playwright e2e, MFA UI, fraud step-up, audit log viewer, runbook, demo.
Success Criteria (end of Day 30)
✓ Zero known double-submit / token-refresh races on money mutations (verified by integration + e2e tests)
✓ Sentry capturing prod errors with Session Replay + sourcemaps; user.id tagged; Web Vitals piped to Sentry Performance
✓ CI pipeline green on every PR (lint, tsc strict, vitest, build, size-limit, lighthouse, e2e)
✓ First-load JS for /dashboard reduced ≥ 30% from Day 1 baseline; LCP p75 < 2.5s; INP p75 < 200ms; CLS p75 < 0.1
✓ Storybook with ≥ 15 stories + visual regression on PR; Playwright e2e covers 4 critical flows
✓ One new feature shipped end-to-end (MFA enrollment + login challenge UI) plus fraud step-up modal wired to backend
✓ 60-day plan drafted from learnings (PWA, i18n, design-system extraction, A/B testing)
Legend
Priority: 🔴 Critical 🟠 High 🟡 Medium 🟢 Low
Effort: hours of focused work (excludes meetings, code review)
Dependencies: Day numbers that must complete first

## 30-Day Roadmap
Day | Date | Phase | Category | Task | Subtasks / Implementation Notes | Files / Areas | Priority | Effort (h) | Depends On | Acceptance Criteria | Risk | Status
1 | Fri 2026-05-01 | Phase 1 – Stabilize | Onboarding | Local environment + repo walkthrough | Clone, copy .env.example → .env.local (NEXT_PUBLIC_API_BASE_URL → backend, Sentry DSN placeholder). pnpm install. pnpm dev. Boot backend in parallel (cd ../backend && docker compose up). Verify login → dashboard → wallet flow. Walk src/app/(auth), src/app/dashboard, src/components/{wallet,community,settings,ui}, src/services/api.ts, src/lib/axios.ts, src/hooks/useAuth.ts. Run Lighthouse against /, /login, /dashboard and save baseline. | package.json, src/app/**, src/components/**, src/services/api.ts, src/lib/axios.ts | 🟠 High | 6 | — | App runs locally talking to backend; can sign in, view wallet balance, navigate dashboard. baseline_lighthouse_day1.html committed. | Low | Not Started
2 | Mon 2026-05-04 | Phase 1 – Stabilize | Discovery | User-flow read-through + UX threat model | Trace login → OTP → dashboard → wallet → transfer end-to-end through src/. Sketch sequence diagram. List every mutation that lacks idempotency / debounce. List every place client state can desync from server (post-transfer balance, member list after add). Inventory localStorage/sessionStorage writes; document where tokens live and the threat trade-off. | src/app/**, src/services/api.ts, src/lib/axios.ts, src/hooks/useAuth.ts, src/lib/store.ts | 🟠 High | 7 | 1 | Sequence diagram + 1-page UX threat model committed to docs/ux_threat_model.md. | Low | Not Started
3 | Tue 2026-05-05 | Phase 1 – Stabilize | Bug Fix | Idempotent client mutations (anti-double-submit) | Add Idempotency-Key UUID header (matched to backend Day 3) on every money mutation via a useMoneyMutation wrapper around React Query. Disable submit buttons while isPending. Wrap dialog confirm actions in single-flight guard. Audit Wallet, Community pay, Events pay dialogs. | src/lib/axios.ts, src/hooks/useMoneyMutation.ts (new), src/components/wallet/**, src/components/dialogs/**, src/components/community/** | 🔴 Critical | 6 | 2 | Spamming a transfer button issues exactly one network call. Idempotency-Key visible in axios request headers (DevTools). | Medium | Not Started
4 | Wed 2026-05-06 | Phase 1 – Stabilize | Bug Fix | Auth token refresh + axios interceptor hardening | Audit src/lib/axios.ts. Implement single-inflight refresh: queue 401s, run one refresh, replay queue. Hard 401 (refresh failed) → clear store → redirect /login. Test rapid concurrent 401s. Move tokens to httpOnly cookies if backend supports it; otherwise document trade-off in threat model. | src/lib/axios.ts, src/lib/store.ts, src/hooks/useAuth.ts, src/components/Protected.tsx | 🔴 Critical | 7 | 3 | 5 simultaneous 401s trigger 1 refresh and 5 successful retries. Failed refresh redirects to /login with cleared store. Test runs 10x without flakes. | High | Not Started
5 | Thu 2026-05-07 | Phase 1 – Stabilize | Observability | Sentry browser SDK + Session Replay + source maps | Add @sentry/nextjs via npx @sentry/wizard@latest -i nextjs. Configure sentry.{client,server,edge}.config.ts. Session Replay: 10% sample, 100% on error. Tag user.id once authenticated via Sentry.setUser. Source-map upload via withSentryConfig in next.config.ts. /sentry-debug route gated on NODE_ENV!=='production'. | next.config.ts, sentry.{client,server,edge}.config.ts, src/app/layout.tsx, src/components/Providers.tsx | 🔴 Critical | 5 | 1 | Throwing in /sentry-debug surfaces a sourcemapped stack in Sentry. Replay attached. user.id tag visible after login. | Low | Not Started
6 | Fri 2026-05-08 | Phase 1 – Stabilize | Testing | Vitest + RTL + MSW: smoke tests for auth & money paths | Install vitest + @testing-library/react + jsdom + msw. Add vitest.config.ts with @ alias. Tests: (a) axios interceptor refreshes once for concurrent 401s; (b) transfer button disables on submit, only one POST fires; (c) useAuth redirects to /login on hard 401; (d) useCurrency renders ₦ correctly. | vitest.config.ts, src/test/setup.ts, src/lib/axios.test.ts, src/hooks/useAuth.test.ts, src/components/wallet/__tests__/ | 🟠 High | 7 | 3,4 | ≥ 4 tests passing repeatedly (run 10x). MSW intercepts all network in tests. | Medium | Not Started
7 | Mon 2026-05-11 | Phase 1 – Stabilize | Review | Week 1 retrospective + PR merge train | Open PRs for Days 3–6 (split by concern). Self-review with /review skill. Merge to main with semver tag v1.0.0-rc1. Write Week 1 retro: what surprised you, what's still scary in the client. Create docs/MATURITY_ASSESSMENT_FRONTEND.md mirroring backend's. | PRs, docs/MATURITY_ASSESSMENT_FRONTEND.md | 🟡 Medium | 4 | 3,4,5,6 | All Phase 1 PRs merged. Tag pushed. Retro doc committed. | Low | Not Started
8 | Tue 2026-05-12 | Phase 2 – Harden | Cleanup | Replace console.log; design-token sweep; barrel-file tidy | Sweep console.* calls in src/ to a central src/lib/logger.ts that fans to Sentry breadcrumbs in prod. Migrate hard-coded color/spacing literals into Tailwind tokens. Centralize toast strings in src/constants/messages.ts. Audit components/ui barrel for re-exports. | src/lib/logger.ts (new), src/constants/messages.ts (new), src/components/**, tailwind.config.ts | 🟡 Medium | 5 | 7 | grep -RIn 'console\.' src/ returns zero non-logger uses. Toast strings defined in one place. | Low | Not Started
9 | Wed 2026-05-13 | Phase 2 – Harden | Type Safety | TypeScript strict + zod schemas from OpenAPI | Enable strict, noUncheckedIndexedAccess, exactOptionalPropertyTypes in tsconfig.json. Generate zod schemas + typed client from backend docs/swagger.json using openapi-zod-client. Replace any in src/services/api.ts with generated types. Validate API responses at the boundary in dev. | tsconfig.json, src/services/api.ts, src/services/generated/** (new), package.json | 🟠 High | 6 | 7 | tsc --noEmit clean under strict. Generated client used by ≥ 3 hooks. Zero `any` in src/services/. | Medium | Not Started
10 | Thu 2026-05-14 | Phase 2 – Harden | Infra | CI pipeline (GitHub Actions) | Create .github/workflows/frontend-ci.yml: setup-node 20 + pnpm cache, run pnpm lint, pnpm tsc --noEmit, pnpm test (vitest), pnpm build (NEXT_TELEMETRY_DISABLED=1), size-limit budget gate. PR check required. | .github/workflows/frontend-ci.yml, .size-limit.json, .nvmrc | 🔴 Critical | 6 | 6,9 | PR opened against main runs full CI; failing build/lint/test/type/size blocks merge. | Low | Not Started
11 | Fri 2026-05-15 | Phase 2 – Harden | Observability | Error boundaries + Web Vitals + structured client logs | Add route segment error.tsx for /dashboard, /wallet, /community plus a global root error.tsx. Each reports to Sentry with route metadata. useReportWebVitals (FCP, LCP, INP, CLS, TTFB) → Sentry Performance. Logger attaches X-Request-ID echoed back from backend. | src/app/error.tsx, src/app/dashboard/error.tsx, src/app/wallet/error.tsx, src/app/community/error.tsx, src/lib/logger.ts, src/lib/web-vitals.ts (new) | 🟠 High | 5 | 5,10 | Forced render error caught by boundary, logged to Sentry. Web Vitals visible in Sentry Performance. | Low | Not Started
12 | Mon 2026-05-18 | Phase 2 – Harden | Security | CSP + security headers via Next config | headers() in next.config.ts: strict CSP (with nonces for inline), HSTS, X-Frame-Options DENY, Referrer-Policy strict-origin-when-cross-origin, Permissions-Policy minimum. Audit all dangerouslySetInnerHTML. Audit third-party scripts for SRI / allowlist. Roll out CSP in Report-Only first. | next.config.ts, src/middleware.ts (nonce injection), src/app/layout.tsx | 🟠 High | 5 | 10 | securityheaders.com grade A on staging. CSP has no unsafe-inline for scripts. App still works after enforce. | Medium | Not Started
13 | Tue 2026-05-19 | Phase 2 – Harden | Security | Dependency + secret scan | Add audit-ci (HIGH gate) + pnpm audit --prod in CI. Add trufflehog for current tree + git history. Replace deprecated transitive deps. Pin Node version via .nvmrc. | .github/workflows/frontend-ci.yml, .nvmrc, package.json | 🟠 High | 5 | 10 | audit-ci HIGH count = 0. trufflehog clean. Node version pinned and used in CI. | Medium | Not Started
14 | Wed 2026-05-20 | Phase 2 – Harden | Review | Week 2 retro + threat model update | Merge train for Phase 2 PRs. Re-run UX threat model from Day 2 — what's now mitigated? Update docs/MATURITY_ASSESSMENT_FRONTEND.md. Tag v1.0.0-rc2. | docs/, PRs, git tag | 🟡 Medium | 4 | 8,9,10,11,12,13 | Retro doc updated. Tag pushed. Phase 2 board cleared. | Low | Not Started
15 | Thu 2026-05-21 | Phase 3 – Optimize | Performance | Bundle analysis + heavy-dep audit | Add @next/bundle-analyzer. ANALYZE=true pnpm build. Identify heavy imports (date-fns full vs date-fns/format, lucide-react default vs named). Flag oversized client components that could be Server Components. Output: docs/bundle_audit.md. | next.config.ts, docs/bundle_audit.md | 🟠 High | 7 | 10 | Audit doc lists ≥ 5 reduction opportunities with file:line + estimated KB savings. | Low | Not Started
16 | Fri 2026-05-22 | Phase 3 – Optimize | Performance | Code splitting + RSC migration + tree-shaking | Convert eligible read-only views to Server Components (dashboard summary cards, community feed list shell). next/dynamic for dialogs and chart libs. Migrate lucide-react to per-icon imports. Replace any wildcard date-fns import with named. Re-run analyzer; document delta. | src/app/dashboard/**, src/components/community/**, src/components/dialogs/**, src/lib/utils.ts | 🟠 High | 7 | 15 | First-load JS for /dashboard ≥ 30% smaller than baseline. RSC count > Client component count on /dashboard. | Medium | Not Started
17 | Mon 2026-05-25 | Phase 3 – Optimize | Performance | React Query strategy + SSR hydration | Set per-query staleTime / gcTime. Prefetch on link hover (router.prefetch + queryClient.prefetchQuery) for /wallet, /community/[id]. Use Next + RQ HydrationBoundary to ship initial dashboard data with SSR HTML. Add @tanstack/react-query-devtools (dev only). Document cache rules in docs/data_layer.md. | src/components/Providers.tsx, src/app/dashboard/page.tsx, src/app/community/[id]/page.tsx, docs/data_layer.md | 🟡 Medium | 6 | 16 | Dashboard renders meaningful data without a client-side spinner on cold visit. Cache hits visible in devtools. | Medium | Not Started
18 | Tue 2026-05-26 | Phase 3 – Optimize | Performance | Image + font optimization | Migrate every <img> to next/image with width/height. Convert PNGs in /public to WebP/AVIF. All fonts via next/font (no <link> tags). priority on hero/LCP image only. Verify CLS goes to ~0. | src/components/**, src/app/layout.tsx, public/** | 🟡 Medium | 5 | 16 | Zero raw <img> tags in src/. Lighthouse CLS < 0.05 across audited routes. | Low | Not Started
19 | Wed 2026-05-27 | Phase 3 – Optimize | Reliability | Route caching + revalidation strategy | Set per-route dynamic + revalidate config in app router. Tag-based revalidation (revalidateTag) for community and wallet reads. Edge runtime for read-only public pages (landing). Document cache map in docs/cache_strategy.md. | src/app/**/page.tsx, src/lib/api/tags.ts (new), docs/cache_strategy.md | 🟡 Medium | 5 | 17 | Public landing TTFB < 200ms from edge. Mutations correctly invalidate tagged caches (verified test). | Medium | Not Started
20 | Thu 2026-05-28 | Phase 3 – Optimize | Performance | Lighthouse CI baseline + Web Vitals gates | Add @lhci/cli to CI on a staging deploy. Capture Lighthouse for /, /login, /dashboard, /wallet, /community. Output: docs/lighthouse_baseline.md. Set CI thresholds (warn-only week 1, then enforce) for LCP, INP, CLS. | .lighthouserc.js, .github/workflows/frontend-ci.yml, docs/lighthouse_baseline.md | 🟠 High | 5 | 18,19 | Baseline doc with per-route scores; CI warns on regression > 10%. | Low | Not Started
21 | Fri 2026-05-29 | Phase 3 – Optimize | Observability | Browser tracing → backend (OTel propagation) | Sentry browser tracing (or @opentelemetry/sdk-trace-web). Start a span on click + navigate + fetch. Propagate traceparent header to backend (mirrors backend Day 21 OTel). Custom marks: 'transfer-submitted' → 'balance-reflected'. | src/lib/axios.ts, src/lib/tracing.ts (new), sentry.client.config.ts | 🟡 Medium | 5 | 5,11,16 | A user-initiated transfer produces a single trace ID spanning browser → backend → Celery task. | Low | Not Started
22 | Mon 2026-06-01 | Phase 4 – Advance | Feature | Storybook + visual regression | Install Storybook 8 (or Ladle). Stories for components/ui/* (Button, Input, Dialog, Switch, Avatar, Select), shared dialogs, wallet card. Hook Chromatic (or Playwright snapshots) for visual regression on PR. Publish Storybook in CI. | .storybook/, src/components/**/*.stories.tsx, .github/workflows/frontend-ci.yml | 🟠 High | 6 | 14 | ≥ 15 stories. Visual regression triggers on a deliberately tweaked button color. | Low | Not Started
23 | Tue 2026-06-02 | Phase 4 – Advance | Feature | Playwright e2e for critical flows | Install @playwright/test. Specs: (a) login → OTP → dashboard; (b) view wallet, initiate transfer, see balance update; (c) join community → pay bill; (d) settings → change password. Run against ephemeral preview deploy. Trace + video on failure. | tests/e2e/, playwright.config.ts, .github/workflows/frontend-ci.yml | 🟠 High | 7 | 10,17 | 4 e2e specs pass on CI 10x without flake. Traces uploaded as CI artifacts. | Medium | Not Started
24 | Wed 2026-06-03 | Phase 4 – Advance | Feature | Step-up auth UI for fraud-flagged transfers | Mirror backend Day 24 fraud_service. Detect 202 / requires_review / requires_step_up responses; render step-up modal (TOTP code) or 'transfer pending review' state. Polling for review outcome with backoff + cancel-on-unmount. | src/components/wallet/StepUpModal.tsx (new), src/components/wallet/TransferDialog.tsx, src/services/api.ts | 🟠 High | 7 | 23 | Forcing the backend fraud rule renders the step-up flow; correct TOTP completes the transfer; pending state shows polling. | High | Not Started
25 | Thu 2026-06-04 | Phase 4 – Advance | Feature | TOTP MFA enrollment + login flow UI | Pages: /settings/security/mfa (enroll → QR → verify → recovery codes download), /(auth)/mfa challenge step. qrcode.react for QR. Recovery codes downloadable .txt + clipboard copy. Disable flow with re-auth. | src/app/settings/security/mfa/page.tsx, src/app/(auth)/mfa/page.tsx, src/components/settings/MfaEnroll.tsx | 🟠 High | 7 | 23 | User enrolls, logs in with TOTP, downloads recovery codes, disables MFA. All paths covered by an e2e spec. | Medium | Not Started
26 | Fri 2026-06-05 | Phase 4 – Advance | Architecture | API client versioning + feature flags | Switch generated client base to /api/v2 stable + opt-in /api/v3 per feature. Build feature-flag util (env-driven first; document upgrade path to LaunchDarkly/Statsig). Deprecation banner component fed by backend Deprecation header. | src/services/api.ts, src/lib/flags.ts (new), src/components/layout/DeprecationBanner.tsx | 🟡 Medium | 4 | 9,14 | A flag flip routes one screen to /api/v3. Banner renders when Deprecation header present. | Low | Not Started
27 | Mon 2026-06-08 | Phase 4 – Advance | Reliability | Optimistic updates + offline retry queue | Optimistic updates for wallet transfer, community join, message-like actions. Offline queue using @tanstack/query-async-storage-persister + onlineManager. User-visible 'queued — will retry' indicator. Exponential backoff via React Query retry + retryDelay. | src/components/Providers.tsx, src/components/wallet/**, src/components/layout/OfflineBanner.tsx (new) | 🟡 Medium | 5 | 17 | Toggling DevTools offline, submitting a transfer, then going online drains the queue and the transfer completes once. | Medium | Not Started
28 | Tue 2026-06-09 | Phase 4 – Advance | Compliance | Audit log viewer + privacy surfacing | Admin page rendering backend audit_events with filter by actor/action/date. CSV export. Surface privacy/terms links in footer + first-login modal. Cookie consent if analytics added. | src/app/admin/audit/page.tsx, src/components/admin/AuditTable.tsx, src/components/layout/Footer.tsx | 🟠 High | 6 | 23 | Audit page renders ≥ 100 rows with pagination + filters. CSV export validated. | Medium | Not Started
29 | Wed 2026-06-10 | Phase 4 – Advance | Documentation | Runbook + ARCHITECTURE.md + Storybook polish | docs/frontend_runbook.md: common alerts (Sentry replay spike, Lighthouse regression, build failure, CSP violation, 401 storm). docs/frontend_architecture.md with C4 (containers + components). Storybook polish: a11y addon, viewport addon, controls. | docs/frontend_runbook.md, docs/frontend_architecture.md, .storybook/ | 🟡 Medium | 5 | 21,22,28 | Runbook covers ≥ 5 alert types. Storybook a11y panel green for all components/ui/* stories. | Low | Not Started
30 | Thu 2026-06-11 | Phase 4 – Advance | Review | Demo, retrospective, 60-day plan | Live demo: signup, MFA, fraud step-up, community pay, audit log. Retro doc: what shipped, what slipped, what surprised. 60-day plan: PWA + service worker, i18n (en/yo/ig), A/B testing, design-system extraction to a shared package, mobile RN bridge. | docs/retro_30d_frontend.md, docs/plan_60d_frontend.md | 🟠 High | 5 | 23,24,25,28,29 | Demo recorded. Retro and 60-day plan committed. Tag v1.1.0. | Low | Not Started

## Phase Milestones
Phase Milestones & Deliverables
Phase | End-of-Phase Deliverable | Acceptance Gate | Owner | Stakeholder Sign-off
Phase 1 – Stabilize | v1.0.0-rc1 with anti-double-submit money mutations, hardened auth refresh, Sentry+Replay, Vitest+RTL+MSW smoke tests. | Refresh-race test passes 10x; Sentry receives sourcemapped exception with Replay; transfer button can't double-submit (test). | Lead Frontend | CTO
Phase 2 – Harden | v1.0.0-rc2 with green CI, TS strict + zod-from-OpenAPI, error boundaries, Web Vitals to Sentry, security headers grade A, dep scan. | PR cannot merge with failing CI; audit-ci HIGH = 0; CSP enforced and verified by curl -I; tsc --noEmit clean. | Lead Frontend | Security
Phase 3 – Optimize | Bundle audit closed; first-load JS reduced ≥ 30% on /dashboard; Lighthouse CI baseline; browser→backend trace propagation. | Lighthouse Performance ≥ 90 on /dashboard; LCP p75 < 2.5s; INP p75 < 200ms; trace ID propagates through Celery task. | Lead Frontend | CTO + Ops
Phase 4 – Advance | v1.1.0 with Playwright e2e, MFA UI, fraud step-up modal, audit log viewer, Storybook + visual regression, runbook, 60-day plan. | Demo passes acceptance script; runbook reviewed by ops; e2e green 10x; MFA enrollment covered by e2e + Storybook. | Lead Frontend | CTO + Compliance

## Risk Register
Risk Register
ID | Risk | Likelihood | Impact | Mitigation | Owner | Trigger Day
R1 | Auth interceptor refactor (Day 4) breaks existing sessions in prod | Low | High | Ship behind a feature flag (RQ middleware toggle); deploy to staging first; canary 10% of traffic for 24h before full rollout; keep old interceptor importable for one release. | Lead Frontend | 4
R2 | TS strict + zod runtime validation (Day 9) creates large red-squiggle backlog and slows feature work | High | Medium | File-by-file ratchet via tsconfig 'include'/'exclude'; allowlist legacy files until Phase 3; runtime zod validation only in dev mode initially. | Lead Frontend | 9
R3 | CSP rollout (Day 12) blocks legitimate scripts (Sentry, analytics, inline tags) | Medium | High | Roll out in Content-Security-Policy-Report-Only header for 48h; collect violations via report-uri; only flip to enforce after zero unexpected reports. | Lead Frontend | 12
R4 | RSC migration (Day 16) regresses interactivity (lost client state, hydration mismatch) | Medium | Medium | Convert leaf read-only components first; keep stateful wrappers as Client Components; add hydration mismatch check to Sentry; revert per-route if Lighthouse regresses. | Lead Frontend | 16
R5 | Step-up auth (Day 24) + MFA (Day 25) confuse users with no MFA enrolled | Medium | High | MFA strictly opt-in; clear in-app copy + tooltip; recovery codes mandatory at enrollment; e2e covers 'no MFA' login path. | Lead Frontend + Design | 25
R6 | Lighthouse CI gates (Day 20) flake on PRs due to network variance | High | Low | Warn-only for week 1; use median of 3 runs; enforce only p75 thresholds; allow CI override label for known-noisy PRs. | Lead Frontend | 20
R7 | 30 days is aggressive — at least one phase will slip | High | Low | Implicit buffer in non-merge days. If slipping, drop Phase 4 polish (Storybook visual regression, audit log viewer) before sacrificing Phase 1 / 2. | Lead Frontend | 14
R8 | Backend OpenAPI (docs/swagger.json) drifts from runtime, breaking generated zod client | Medium | Medium | Add a CI job that regenerates the client and fails on diff; coordinate with backend lead for spec freezes around release tags. | Lead Frontend + Backend | 9
R9 | Knowledge gaps from previous owner (undocumented design decisions, magic state) | High | Medium | Day 2 includes a UX read-through. Day 29 builds the runbook. Schedule 1h with previous owner if reachable. | Lead Frontend | 1

## KPIs & Metrics
KPIs & Success Metrics
Metric | Baseline (Day 0) | Target (Day 30) | Measurement Source | Notes
Lighthouse Performance score on /dashboard | TBD (capture Day 1) | ≥ 90 | Lighthouse CI | Median of 3 runs; p75 enforced from Day 20
LCP on /dashboard (p75) | TBD | < 2.5s | Lighthouse + RUM (Sentry) | Phase 3 target; gated in CI from Day 20
INP (p75) | TBD | < 200ms | Sentry RUM | Day 11 wires Web Vitals; Day 20 sets gate
CLS (p75) | TBD | < 0.1 | Lighthouse + RUM | Day 18 image/font fix is the big lever
First-load JS for /dashboard | TBD | ≥ 30% reduction vs baseline | @next/bundle-analyzer | Day 15 baseline; Day 16 RSC migration is the lever
Test coverage (src/lib + src/hooks) | 0% | ≥ 70% | vitest --coverage | Day 6 sets up framework; ratchet up through Phases 2–3
e2e specs passing on CI | 0 | ≥ 4 | Playwright | Day 23 ships first 4; Day 25 adds MFA
Sentry coverage of unhandled exceptions | 0% | 100% in prod-mode env | Sentry | Verified via /sentry-debug; Day 5
TypeScript strict mode | Off | On with 0 `any` in src/services/ | tsc --noEmit | Day 9; CI gated from Day 10
CI pipeline pass rate | n/a (no CI) | 100% on main, < 10% flake on PR | GitHub Actions | Bundle/Lighthouse warn-only for week 1
HIGH/CRITICAL audit-ci findings | TBD | 0 | audit-ci in CI | Day 13
securityheaders.com grade on staging | F | A | securityheaders.com | Day 12 CSP rollout
Storybook stories | 0 | ≥ 15 (with a11y panel green) | Storybook + addon-a11y | Days 22 + 29
Documented frontend runbook | None | Covers ≥ 5 alert types | docs/frontend_runbook.md | Day 29
Mean time to detect prod incident | Unknown | < 5 min via Sentry alert | Sentry alert rules | After Day 5

## Tech Stack Additions
New Tools & Libraries Introduced
Tool / Library | Purpose | Introduced Day | Add to | Notes
@sentry/nextjs | Browser + server error tracking, Session Replay, source maps, perf | 5 | package.json (prod) | Use sentry-wizard; tracesSampleRate=0.1
vitest + @testing-library/react + jsdom | Unit / component tests | 6 | package.json (dev) | Faster than Jest; aligns with Vite ecosystem
msw | Network mocking in tests | 6 | package.json (dev) | Service-worker mode for browser tests later
openapi-zod-client + zod | Generate typed API client + runtime validation from backend swagger.json | 9 | package.json (prod+dev) | Regenerate in CI on backend spec change
size-limit | Bundle size budgets in CI | 10 | package.json (dev) | Fail PR on > 5% growth without label override
audit-ci | Dep vulnerability scan in CI | 13 | CI only | Block on HIGH
trufflehog | Secret scan in CI + git history | 13 | CI only | Pre-commit hook also recommended
@next/bundle-analyzer | Visualize JS bundles | 15 | package.json (dev) | ANALYZE=true pnpm build
@tanstack/react-query-devtools | Inspect query cache in dev | 17 | package.json (dev) | Tree-shaken from prod build
@lhci/cli | Lighthouse CI in pipeline | 20 | CI only | Median of 3 runs; p75 thresholds
@opentelemetry/sdk-trace-web (or Sentry browser tracing) | Browser → backend trace propagation | 21 | package.json (prod) | Mirrors backend Day 21 OTel
Storybook 8 (or Ladle) | UI component dev environment + visual regression | 22 | package.json (dev) | Chromatic or Playwright snapshots for VR
@playwright/test | Browser e2e | 23 | package.json (dev) | Trace + video on failure; Chromium + WebKit matrix
qrcode.react | TOTP enrollment QR | 25 | package.json (prod) | Server returns otpauth:// URI
@tanstack/query-async-storage-persister | Offline mutation queue | 27 | package.json (prod) | Pair with onlineManager

## Effort Summary
Effort Summary (focused hours per day, excludes meetings/review)
Phase | Days | Total Effort (h) | Avg Effort/Day (h)
Phase 1 – Stabilize | 7 | 42 | 6
Phase 2 – Harden | 7 | 36 | 5.1
Phase 3 – Optimize | 7 | 40 | 5.7
Phase 4 – Advance | 9 | 52 | 5.8
TOTAL | 30 | 170 | 5.7