## Executive Summary
CCP-Frontend — UI/UX Modernization Roadmap (30 working days)
Owner: Lead Frontend Developer (engineer-led design) ¦ Start: 2026-06-12 ¦ End: 2026-07-23
Mission
Take the existing Next.js 15 / shadcn / Tailwind v4 client and modernize it end-to-end: a coherent design language (tokens for color, type, space, motion), a refreshed component library, screen-level redesigns of every major flow, first-class mobile + dark mode, and WCAG 2.1 AA conformance on top screens. Runs after the engineering hardening plan (which ends 2026-06-11) so we modernize on top of TS strict, CI, Sentry, and a perf budget — not under them.
Scope assumptions (change if wrong)
• Full overhaul (visual + IA + flows + empty/loading/error states + dark mode + mobile-first), not just a paint job. • Engineer-led: no separate Figma → handoff phase. Decisions made in code with reference apps (Geist, Stripe, Linear, Wise). • Builds on existing stack: shadcn/ui + Radix + Tailwind v4 + lucide. Augmented with framer-motion, next-themes, sonner, vaul, cmdk, Geist font. • Brand identity is not being re-created from scratch — direction is picked from CCPAY brand reference + 3 mood boards on Day 5.
Phases
Phase | Window | Focus
Phase 1 – Audit & Direction | Days 1–6 | Heuristic + a11y audit, IA + flow review, competitive teardown, mood-board pick, modernization brief sign-off.
Phase 2 – Foundations | Days 7–13 | Design tokens (color, type, space, radius, shadow), iconography, motion system, dark mode, theme switcher, primitives refresh.
Phase 3 – Components | Days 14–20 | Overlays, forms, data display, feedback patterns, navigation, onboarding, auth screens redesign.
Phase 4 – Screen Redesign | Days 21–27 | Dashboard, wallet, community, bills, settings, mobile pass, notifications + receipts redesigned.
Phase 5 – Polish & QA | Days 28–30 | WCAG 2.1 AA pass, cross-browser/device QA + visual regression, design-review demo + 60-day follow-on.
Success Criteria (end of Day 30)
✓ Design tokens (color/type/space/radius/shadow/motion) defined in tailwind.config + CSS variables; every component reads from tokens.
✓ Dark mode shipped across 100% of redesigned screens via next-themes; theme switcher in header; respects system preference.
✓ Every major screen redesigned: auth (login/OTP/MFA), dashboard, wallet (balance + transactions + transfer), community (feed + detail + pay), bills, settings, profile, notifications.
✓ Mobile-first pass: bottom-tab nav, thumb-zone CTAs, vaul sheets for mobile dialogs, all screens usable at 360px width.
✓ Loading: skeletons (not spinners) on all data-bound screens. Empty states with clear CTAs. Error states with recovery actions.
✓ Motion system live: framer-motion presets for enter/exit, page transitions, micro-interactions; respects prefers-reduced-motion.
✓ WCAG 2.1 AA conformance verified on top 10 screens via axe + pa11y + manual screen-reader pass; Lighthouse Accessibility ≥ 95.
✓ Storybook (from engineering Day 22) covers ≥ 30 redesigned components with a11y panel green.
✓ 5-user usability test on the redesigned dashboard + transfer flow; findings logged.
✓ 60-day plan drafted (PWA, i18n, illustration system, in-app product tour).
Legend
Priority: 🔴 Critical 🟠 High 🟡 Medium 🟢 Low
Effort: hours of focused design + implementation work
Dependencies: Day numbers that must complete first

## 30-Day Roadmap
Day | Date | Phase | Category | Task | Subtasks / Implementation Notes | Files / Areas | Priority | Effort (h) | Depends On | Acceptance Criteria | Risk | Status
1 | Fri 2026-06-12 | Phase 1 – Audit & Direction | Audit | Heuristic audit + screenshot inventory of every screen and state | Walk every route in src/app and capture screenshots of: empty / loading / data / error / success states. Inventory in docs/ux_audit/ as one folder per screen. Score against Nielsen's 10 heuristics. Tag every issue (consistency, feedback, recovery, IA, visual). | src/app/**, docs/ux_audit/inventory.md | 🟠 High | 5 | — | Inventory MD lists every route with screenshots of ≥ 3 states. Heuristic score sheet committed (≥ 30 issues identified). | Low | Not Started
2 | Mon 2026-06-15 | Phase 1 – Audit & Direction | Audit | User flow + IA review | Map every flow as a step-by-step diagram: signup → OTP → KYC, login → dashboard, wallet view → transfer → confirm → receipt, community discover → join → pay. Identify dead ends, redundant steps, missing back/cancel paths. Sketch a revised IA tree. | docs/ux_audit/flows.md, docs/ux_audit/ia_tree.md | 🟠 High | 6 | 1 | 5 flow diagrams + 1 IA tree committed. Each flow lists ≥ 2 friction points and a proposed fix. | Low | Not Started
3 | Tue 2026-06-16 | Phase 1 – Audit & Direction | Research | Competitive teardown of modern fintech UIs | Capture annotated screenshots from Wise, Revolut, Cash App, Kuda, Opay, Stripe Dashboard, Linear, Vercel. Document patterns to steal: balance hero card, transaction list density, transfer review screen, empty states, mobile bottom-tab, motion, dark mode. One slide per pattern. | docs/ux_audit/competitive_teardown.md | 🟡 Medium | 5 | — | Teardown doc with ≥ 20 annotated patterns categorized as adopt / adapt / reject for CCPay. | Low | Not Started
4 | Wed 2026-06-17 | Phase 1 – Audit & Direction | Accessibility | Accessibility baseline (axe, pa11y, screen reader, keyboard) | Add @axe-core/react in dev. Run pa11y on /, /login, /dashboard, /wallet, /community, /settings. VoiceOver / NVDA pass on login + transfer flow. Capture: contrast violations, missing alt/labels, focus traps, skipped headings. Output: docs/ux_audit/a11y_baseline.md. | src/components/Providers.tsx (axe), pa11y.config.json, docs/ux_audit/a11y_baseline.md | 🟠 High | 6 | 1 | Baseline doc with per-route a11y score + ≥ 15 categorized findings (severity-tagged). | Medium | Not Started
5 | Thu 2026-06-18 | Phase 1 – Audit & Direction | Direction | Brand & visual direction — 3 mood boards, pick one | Build 3 mood boards (Notion-style minimal / Linear-dense / Wise-warm-fintech). Each: hero color, neutral palette, type pairing, motion mood, illustration style. Reference CCPAY_Brand_Reference.docx if available. Pick one with the team. Document the chosen direction. | docs/ux_audit/mood_boards/, docs/ux_audit/direction.md | 🟠 High | 5 | 2,3 | 3 boards rendered as PNGs. Direction doc committed with a one-paragraph rationale and the chosen board labeled. | Medium | Not Started
6 | Fri 2026-06-19 | Phase 1 – Audit & Direction | Review | Modernization brief sign-off | Synthesize Days 1–5 into docs/modernization_brief.md: scope, direction, principles (e.g. 'fast > pretty', 'mobile-first', 'a11y is non-negotiable'), success metrics, what's out of scope. Sign-off from CTO + product. Tag baseline_pre_modernization for screenshot diffs. | docs/modernization_brief.md, git tag baseline_pre_modernization | 🔴 Critical | 4 | 1,2,3,4,5 | Brief committed and approved in PR. Baseline tag pushed. | Low | Not Started
7 | Mon 2026-06-22 | Phase 2 – Foundations | Tokens | Color system — semantic tokens + CSS variables | Define semantic tokens (brand, neutral 0-1000, accent, success, warning, danger, info, surface, surface-elevated, border, ring) as CSS variables in globals.css. Both light and dark sets. Tailwind v4 @theme to expose. Replace every hard-coded color in src/. | src/app/globals.css, tailwind.config.ts, src/components/** | 🔴 Critical | 6 | 6 | Zero hex/rgb literals in src/components. Color tokens documented in docs/design_system/colors.md with swatches. | Medium | Not Started
8 | Tue 2026-06-23 | Phase 2 – Foundations | Tokens | Typography scale + font pairing | Install Geist (or Inter) via next/font. Type scale as Tailwind tokens: display-2xl, display-xl, display-lg, h1-h4, body-lg/md/sm, caption, code. Line-height + tracking baked in. Define text-color tokens (text-primary, secondary, muted, on-brand). Replace ad-hoc font sizes. | src/app/layout.tsx (next/font), tailwind.config.ts, src/app/globals.css | 🟠 High | 5 | 7 | Type scale documented + applied. Headings consistent across /dashboard, /wallet, /community. | Low | Not Started
9 | Wed 2026-06-24 | Phase 2 – Foundations | Tokens | Spacing, radius, shadow scales | Lock the Tailwind spacing scale (4px base). Define radius tokens (sm, md, lg, xl, 2xl, full). Elevation tokens (shadow-xs through shadow-2xl) — modern fintech feel: subtle, low-contrast. Audit src/ for arbitrary values. | tailwind.config.ts, src/components/** | 🟠 High | 5 | 7 | Arbitrary [val] usage in src/ down to < 5 sites. Spacing/radius/shadow scales documented. | Low | Not Started
10 | Thu 2026-06-25 | Phase 2 – Foundations | Iconography | Iconography audit + style decision | Audit lucide-react usage. Decide stroke vs filled. Build src/components/ui/Icon.tsx wrapper that enforces consistent size + stroke-width. Sketch any custom CCPay-specific icons (wallet, community badge) — 4 max. | src/components/ui/Icon.tsx (new), docs/design_system/icons.md | 🟡 Medium | 5 | 8 | All icon usage routed through Icon wrapper. ≤ 4 custom icons added as SVG components. | Low | Not Started
11 | Fri 2026-06-26 | Phase 2 – Foundations | Motion | Motion system — framer-motion + reduced-motion | Install framer-motion. Define motion tokens: durations (fast 150ms, base 250ms, slow 400ms), easings (ease-out for enter, ease-in for exit, spring for delight). Build <Motion> presets: FadeIn, SlideUp, ScaleIn, ListItem (stagger). Wrap in prefers-reduced-motion guard. | src/lib/motion.ts (new), src/components/ui/motion.tsx (new), docs/design_system/motion.md | 🟡 Medium | 6 | 6 | Motion presets documented + used in ≥ 2 places. Reduced-motion turns animations into 0ms transitions. | Medium | Not Started
12 | Mon 2026-06-29 | Phase 2 – Foundations | Theming | Dark mode + theme switcher (next-themes) | Install next-themes. Wire ThemeProvider in src/components/Providers.tsx. Header switcher (system / light / dark). Map every color token to dark mode variant. SSR-safe (no flash). Sentry tag with theme. | src/components/Providers.tsx, src/components/layout/ThemeSwitcher.tsx (new), src/app/layout.tsx | 🟠 High | 5 | 7 | Theme persists across reloads, no FOUC. Switching theme on /dashboard updates all surfaces atomically. | Medium | Not Started
13 | Tue 2026-06-30 | Phase 2 – Foundations | Components | Primitives refresh part 1 — Button, Input, Select, Switch, Avatar, Badge, Card | Refresh the 7 atomic components against new tokens. Variants: Button (primary, secondary, ghost, destructive, link / sm, md, lg / loading state). Input with label + helper + error built in. Select with search. Avatar with status dot. Badge variants. Card with hover/elevation. Stories for each. | src/components/ui/{button,input,select,switch,avatar,badge,card}.tsx, *.stories.tsx | 🔴 Critical | 7 | 7,8,9,11 | All 7 components ship in Storybook with ≥ 3 variants each + a11y panel green. | Medium | Not Started
14 | Wed 2026-07-01 | Phase 3 – Components | Components | Overlays — Dialog, Drawer, Sheet, Toast, Tooltip, Popover (sonner + vaul) | Replace react-hot-toast with sonner. Add vaul for mobile drawers/sheets. Refresh Dialog with focus trap + scroll lock + framer enter/exit. Tooltip + Popover via Radix with token-driven styles. | src/components/ui/{dialog,drawer,sheet,toast,tooltip,popover}.tsx, src/components/Providers.tsx, package.json | 🟠 High | 6 | 13 | Toast unified to sonner. Mobile drawer feels native (rubber-band, swipe-to-dismiss). All overlays a11y-clean. | Medium | Not Started
15 | Thu 2026-07-02 | Phase 3 – Components | Patterns | Form patterns — labels, helper, errors, validation feedback, multi-step | Define a Form primitive (label / control / description / error in one). Inline validation with debounce. Error summaries on submit. Multi-step form scaffold for KYC + signup. Input masks (cleave.js or maska) for amounts and phone numbers. | src/components/ui/form.tsx (new), src/components/forms/MultiStep.tsx (new), package.json | 🟠 High | 7 | 13 | Login + transfer + KYC forms migrated to new primitive. Errors announce to screen readers. | Medium | Not Started
16 | Fri 2026-07-03 | Phase 3 – Components | Patterns | Data display — Table, List, Skeleton, Empty State | Build Table (sortable, sticky header, density toggle). List (virtualized for > 200 rows via @tanstack/react-virtual). Skeletons matching final layout (not generic blocks). EmptyState component (icon + title + body + CTA). | src/components/ui/{table,list,skeleton,empty-state}.tsx, package.json | 🟠 High | 6 | 13 | Skeletons render with no layout shift on hydrate. EmptyState used in Storybook with ≥ 4 example contexts. | Medium | Not Started
17 | Mon 2026-07-06 | Phase 3 – Components | Patterns | Feedback patterns — loading, success, error, confirmation | Replace spinners with skeletons. Inline success states (checkmark + message). Error patterns: inline (form), toast (transient), banner (page-level), full-page (broken). Destructive confirmation dialogs require typing verb (e.g. 'delete'). | src/components/ui/{banner,confirm}.tsx, src/components/wallet/**, src/components/dialogs/** | 🟠 High | 6 | 14,16 | 0 raw spinners outside auth init. Destructive confirms require typed verb. | Medium | Not Started
18 | Tue 2026-07-07 | Phase 3 – Components | Navigation | Navigation — sidebar, topbar, breadcrumb, command palette (cmdk) | Refresh sidebar with collapsible groups + active state. Topbar with search + notifications + theme + avatar menu. Breadcrumb component. Command palette via cmdk (Cmd-K) for navigation, recent transfers, quick actions. | src/components/layout/{Sidebar,Topbar,Breadcrumb,CommandPalette}.tsx, package.json | 🟠 High | 7 | 14 | Cmd-K opens palette, fuzzy-searches across routes + recent items, navigates on Enter. Sidebar collapses to icons. | Medium | Not Started
19 | Wed 2026-07-08 | Phase 3 – Components | Patterns | Onboarding patterns — empty-state CTAs, tooltips, product tour scaffold | Build first-run states for /dashboard, /wallet, /community. Coach-mark tooltip primitive (dismissible, persisted). Product-tour scaffold (driver.js or react-joyride) — content for tour deferred to 60-day plan. Inline 'next step' CTAs on partially-complete profiles. | src/components/onboarding/**, src/lib/onboarding.ts (new), package.json | 🟡 Medium | 6 | 16 | Fresh user lands on a dashboard with non-empty 'getting started' card and ≥ 3 contextual CTAs. | Medium | Not Started
20 | Thu 2026-07-09 | Phase 3 – Components | Screen | Auth screens redesigned — login, signup, OTP, MFA enroll/challenge | Full redesign of /(auth)/* using new tokens + components. Hero panel (left) + form (right) on desktop, full-bleed on mobile. OTP via react-otp-input with auto-advance, paste support. MFA challenge feels distinct from login (security badge). | src/app/(auth)/**, src/components/auth/** | 🔴 Critical | 7 | 13,14,15 | All auth screens use design tokens; passes a11y on focus + label + contrast; mobile is single column with thumb-zone CTA. | Medium | Not Started
21 | Fri 2026-07-10 | Phase 4 – Screen Redesign | Screen | Dashboard redesign — hero balance, quick actions, recent activity, insights | Information density: hero balance card with masked toggle. Quick actions row (Transfer, Top up, Pay bill, Request). Recent activity list (last 10). Insights cards (this month spend, savings progress) — placeholders if data missing. SSR initial data via HydrationBoundary. | src/app/dashboard/page.tsx, src/components/dashboard/** | 🔴 Critical | 7 | 13,14,16,17 | Dashboard renders meaningful content in < 1.5s LCP at p75. New user lands on a non-empty layout with onboarding cues. | Medium | Not Started
22 | Mon 2026-07-13 | Phase 4 – Screen Redesign | Screen | Wallet redesign — balance, transactions, transfer flow | Wallet hero with balance + masked + currency switcher. Transactions: grouped by day, category icons, search, filter, infinite scroll (virtualized). Transfer dialog: 3-step (recipient → amount → review) with inline fee + arrival estimate. Receipt screen with share/download. | src/app/wallet/**, src/components/wallet/** | 🔴 Critical | 7 | 16,17,21 | Transfer flow completes in 3 screens with clear review step. Transaction list scrolls smoothly with 1k items. | High | Not Started
23 | Tue 2026-07-14 | Phase 4 – Screen Redesign | Screen | Community feed + community detail redesign | Feed: card-based with member avatars, unread indicator, last activity. Detail: tabs (Overview, Members, Bills, Activity). Empty states for new communities. Members grid with role badges. Mobile bottom-sheet for quick actions. | src/app/community/**, src/components/community/** | 🟠 High | 7 | 14,16,17 | Feed scrolls smoothly with 100+ items; detail tabs persist in URL; mobile bottom-sheet matches native feel. | Medium | Not Started
24 | Wed 2026-07-15 | Phase 4 – Screen Redesign | Screen | Bills + Payments flow redesign (with confirmation, review, receipt) | Bills list (filter by status), bill detail with member share table, pay flow with confirmation + review + receipt. Receipt is shareable as PNG (canvas) and viewable as URL. Match the refreshed transfer flow patterns. | src/app/community/[id]/bills/**, src/components/community/bills/** | 🟠 High | 6 | 22 | Pay flow shares the 3-step pattern. Receipt PNG renders correctly on mobile share sheet. | Medium | Not Started
25 | Thu 2026-07-16 | Phase 4 – Screen Redesign | Screen | Settings + Profile + Security redesigned | Settings as left-rail nav: Profile, Security (MFA mgmt), Notifications, Preferences (theme, currency display, language placeholder), Data & Privacy. Each section uses Card + form primitives. MFA management uses the QR + recovery code component from engineering Day 25. | src/app/settings/**, src/components/settings/** | 🟠 High | 6 | 20,15,16 | All settings sub-screens use the same chrome and tokens; saving shows inline success. | Low | Not Started
26 | Fri 2026-07-17 | Phase 4 – Screen Redesign | Mobile | Mobile-first responsive pass — bottom-tab nav, sheets, thumb zones | Add bottom-tab nav for mobile (5 tabs: Home, Wallet, Pay, Community, More). Convert dialogs to vaul sheets on < 768px. Audit every screen at 360px width: thumb-zone CTAs, sticky action bars, no horizontal scroll. iOS Safari quirks (100vh, safe areas). | src/components/layout/MobileNav.tsx (new), src/components/dialogs/**, src/app/layout.tsx | 🔴 Critical | 7 | 21,22,23,24,25 | All redesigned screens usable on iPhone SE width (375px). No horizontal overflow. Bottom nav respects safe areas. | High | Not Started
27 | Mon 2026-07-20 | Phase 4 – Screen Redesign | Screen | Notifications + activity timeline + receipts | Notifications drawer (right-side on desktop, bottom-sheet on mobile) with grouping (today/this week/older), unread state, mark-all-read. Activity timeline component reusable for wallet + community. Standalone receipt URL with OG image. | src/components/layout/Notifications.tsx, src/components/ui/Timeline.tsx (new), src/app/r/[id]/page.tsx (new) | 🟡 Medium | 5 | 14,17 | Notification drawer renders ≥ 3 grouped sections; receipt URL has OG preview when shared on WhatsApp/Slack. | Low | Not Started
28 | Tue 2026-07-21 | Phase 5 – Polish & QA | Accessibility | WCAG 2.1 AA pass on top 10 screens | Run axe + pa11y in CI as gates (block PR on serious violations). Manual screen-reader pass on auth + dashboard + transfer + community pay. Keyboard-only walkthrough. Fix focus ring visibility, skipped headings, missing labels. Document conformance in docs/a11y_conformance.md. | .github/workflows/frontend-ci.yml, src/components/**, docs/a11y_conformance.md | 🔴 Critical | 6 | 20,21,22,23,25,26 | Lighthouse Accessibility ≥ 95 on top 10 routes. axe serious violations = 0. Conformance doc signed off. | Medium | Not Started
29 | Wed 2026-07-22 | Phase 5 – Polish & QA | QA | Cross-browser + cross-device QA + visual regression baseline | Test matrix: Chrome, Safari, Firefox × desktop + iOS + Android. Capture Chromatic (or Playwright) baselines for the redesigned routes. Run 5-user usability test (recorded) on dashboard + transfer flow. Triage findings into 'fix now' vs '60-day plan'. | tests/e2e/visual.spec.ts, .chromatic.config, docs/usability_test_findings.md | 🟠 High | 5 | 28 | Visual baselines captured for ≥ 10 routes. Usability findings doc with severity-tagged issues. | Medium | Not Started
30 | Thu 2026-07-23 | Phase 5 – Polish & QA | Review | Design review demo + retro + 60-day follow-on plan | Live demo: before/after for top 5 screens, dark mode toggle, mobile walkthrough, motion examples, command palette. Retro: what worked, what didn't. 60-day plan: PWA + service worker, i18n (en/yo/ig), illustration system, in-app product tour content, design-token export to a shared package, motion library expansion. | docs/retro_modernization.md, docs/plan_60d_modernization.md | 🟠 High | 4 | 26,27,28,29 | Demo recorded. Retro + 60-day plan committed. Tag v2.0.0-design. | Low | Not Started

## Phase Milestones
Phase Milestones & Deliverables
Phase | End-of-Phase Deliverable | Acceptance Gate | Owner | Stakeholder Sign-off
Phase 1 – Audit & Direction | Modernization brief approved with chosen visual direction + a11y baseline + IA tree. | Brief PR merged; baseline tag pushed; ≥ 30 audit findings + ≥ 15 a11y findings logged. | Lead Frontend | CTO + Product
Phase 2 – Foundations | Design tokens (color/type/space/radius/shadow/motion) live in Tailwind + CSS variables. Dark mode + theme switcher shipped. 7 atomic components refreshed. | Zero hex literals in src/components. Theme toggle works without FOUC. Storybook covers ≥ 7 atomic components with a11y green. | Lead Frontend | CTO
Phase 3 – Components | Overlay + form + data + feedback + nav + onboarding patterns refreshed. Auth flow fully redesigned. | Cmd-K palette functional. Toast unified. /(auth) screens use new tokens end-to-end and pass a11y. | Lead Frontend | Product
Phase 4 – Screen Redesign | Dashboard, Wallet, Community, Bills, Settings, Notifications redesigned. Mobile-first pass complete with bottom-tab nav + sheets. | Each redesigned screen passes a 5-checkpoint review (tokens, motion, dark mode, mobile, a11y). LCP p75 < 2.5s preserved. | Lead Frontend | CTO + Product
Phase 5 – Polish & QA | v2.0.0-design tag with WCAG 2.1 AA conformance, visual regression baselines, usability test findings, and 60-day plan. | Lighthouse Accessibility ≥ 95. axe serious violations = 0. Demo passes acceptance script. 5-user test findings triaged. | Lead Frontend | CTO + Compliance

## Risk Register
Risk Register
ID | Risk | Likelihood | Impact | Mitigation | Owner | Trigger Day
R1 | Engineer-led design produces inconsistent visuals (no designer in the loop) | High | Medium | Token discipline: every component reads from tokens, not literals. CI lint rule against hex/rgb in src/components. Reference 3 anchor apps (Geist, Linear, Wise) for every screen review. | Lead Frontend | 7
R2 | Modernization breaks existing user habits, causing support tickets | Medium | High | Day 29 5-user usability test before sign-off. Ship behind a 'new look' feature flag with opt-out for 14 days. In-app comm + changelog. | Lead Frontend + Product | 26
R3 | Scope creep — 'while we're here, let's also redesign X' | High | Medium | Brief on Day 6 lists what's IN and OUT. Anything not listed goes to docs/plan_60d_modernization.md without scope debate. | Lead Frontend | 6
R4 | Half-done dark mode (some screens broken) is worse than no dark mode | Medium | High | Dark mode is gated behind a flag until Day 25 (after every redesigned screen ships). Per-screen dark-mode checklist in PR template. | Lead Frontend | 12
R5 | Animations regress performance (jank, INP > 200ms) | Medium | Medium | framer-motion only on mount/exit + small interactions. GPU-friendly properties only (transform, opacity). prefers-reduced-motion respected. INP gate from engineering Day 20 still enforced. | Lead Frontend | 11
R6 | Accessibility regressions during redesign (focus rings removed, contrast lost) | High | High | axe in dev (Day 4) + axe + pa11y as CI gates from Day 28. PR template includes a11y checklist. Manual SR pass before each phase milestone. | Lead Frontend | 4
R7 | Visual regression noise — every PR shows hundreds of diffs | High | Low | Re-baseline Chromatic at the start of each phase. Use approval workflow per route, not per snapshot. | Lead Frontend | 22
R8 | Mobile-first pass (Day 26) reveals deep layout debt requiring screen rework | Medium | High | Audit mobile during each screen redesign (Days 21–25), not at the end. Day 26 is a polish pass, not a discovery pass. | Lead Frontend | 21
R9 | 30 days is aggressive for full overhaul — at least one phase will slip | High | Low | Implicit buffer in non-merge days. If slipping, drop polish (notifications screen, command palette, illustration system) before sacrificing tokens / dark mode / a11y. | Lead Frontend | 14
R10 | Brand direction debate stalls Phase 1 (mood-board pick) | Medium | Medium | Day 5 has a hard time-box. If no consensus by EOD, pick the safest option (Wise-warm-fintech) and revisit at Day 30 retro. | Lead Frontend + CTO | 5

## KPIs & Metrics
KPIs & Success Metrics
Metric | Baseline (Day 0) | Target (Day 30) | Measurement Source | Notes
Lighthouse Accessibility score (top 10 routes) | TBD (capture Day 4) | ≥ 95 | Lighthouse CI | Day 4 baseline; Day 28 gate
axe serious + critical violations | TBD | 0 | axe-core in CI | Block PR on serious; Day 28
Color contrast violations (WCAG AA) | TBD | 0 across redesigned screens | axe + manual | Token-driven; Day 7
Hex/rgb literals in src/components | TBD | 0 | ESLint custom rule + grep | Token discipline; Day 7
Dark mode coverage of redesigned screens | 0% | 100% | Manual screenshot grid | Per-screen checklist; Day 12 onwards
Mobile usability (360–390px width, top 10 routes) | TBD | All pass mobile checklist | Manual + Playwright viewports | Day 26 + per-screen reviews
Skeleton coverage (data-bound screens) | TBD | 100% | Manual audit | Day 16; replaces spinners
Empty-state coverage (data-bound screens) | TBD | 100% | Manual audit | Day 16 + Day 19
Storybook stories for redesigned components | 0 (or eng baseline) | ≥ 30 with a11y green | Storybook + addon-a11y | Compounds with engineering Day 22
Visual regression baselines (routes) | 0 | ≥ 10 | Chromatic / Playwright | Day 29
INP p75 after motion rollout | Eng baseline | < 200ms (no regression) | Sentry RUM | Day 11 motion guardrail
LCP p75 on /dashboard | Eng baseline | < 2.5s (no regression) | Lighthouse + RUM | Day 21 hero card lever
Usability test severity-1 issues | Unknown | 0 unresolved at sign-off | Day 29 5-user test | Severity-tagged backlog
Time on first task (5-user test) | TBD | ≥ 30% reduction vs pre-redesign | Recorded sessions | Compare against Day 1 baseline
In-app theme switch usage (after launch) | n/a | Tracked via analytics | Sentry / analytics tag | Validate dark mode demand

## Tech Stack Additions
New Tools & Libraries Introduced
Tool / Library | Purpose | Introduced Day | Add to | Notes
@axe-core/react | In-app a11y violations in dev console | 4 | package.json (dev) | Logs to console + Sentry breadcrumb
pa11y-ci | Automated a11y audit per route in CI | 4 | CI only | Run against staging deploy
Geist (or Inter) via next/font | Modern type pairing | 8 | package.json (prod) | self-hosted; no CLS
framer-motion | Motion system (enter/exit, stagger, micro-interactions) | 11 | package.json (prod) | Tree-shake LayoutGroup; respect prefers-reduced-motion
next-themes | Dark mode + system preference + persistence | 12 | package.json (prod) | SSR-safe; no FOUC
sonner | Modern toast (replaces react-hot-toast) | 14 | package.json (prod) | Unified API; better stacking
vaul | Mobile drawer / bottom sheet (native feel) | 14 | package.json (prod) | Replaces Dialog on < 768px
cmdk | Command palette (Cmd-K) | 18 | package.json (prod) | Keyboard-first nav + quick actions
@tanstack/react-virtual | Virtualized lists (transactions, members) | 16 | package.json (prod) | Pair with skeletons for smooth scroll
maska or cleave.js | Input masks for amounts, phone, OTP | 15 | package.json (prod) | Pick maska for smaller bundle
driver.js (or react-joyride) | Product tour scaffold | 19 | package.json (prod) | Content deferred to 60-day plan
Chromatic (or Playwright snapshots) | Visual regression on PR | 29 | CI only | Re-baseline at each phase milestone
html2canvas (or @vercel/og) | Receipt → shareable PNG | 24 | package.json (prod) | OG image for receipt URLs

## Effort Summary
Effort Summary (focused hours per day)
Phase | Days | Total Effort (h) | Avg Effort/Day (h)
Phase 1 – Audit & Direction | 6 | 31 | 5.2
Phase 2 – Foundations | 7 | 39 | 5.6
Phase 3 – Components | 7 | 45 | 6.4
Phase 4 – Screen Redesign | 7 | 45 | 6.4
Phase 5 – Polish & QA | 3 | 15 | 5
TOTAL | 30 | 175 | 5.8